## Sheet1
Week | Important Events | Colin | Michael | Josh M | Josh N
2026-04-02 |  | Mode 7 implementation in C, mario kart scaffolding, test multiplayer game | RT FSM, PL structure | Petalinux image, display out | Awaiting PL tasks from Michael and for Josh M to finalize some Linux stuff
2026-04-09 |  | Debug movement, colors | Test board with PL dev image | Fixed pixel conversion & input, AXI stream test image (WIP) | Redirected by PS changes.
2026-04-16 |  | Finish game (30+ hours in one week; game is almost steam-ready). Starting poster, website and final report | Wire up remaining simple PL feature, Dispatch Unit | AXI Stream -> DMA -> Screen pipeline implemented | Redirected from poster, website, report tasks to audio
2026-04-25 | Last day for poster submission | Poster work, additional bug testing in game | Finish dispatch unit, render tiles | AXI4-S implementation | Completed audio as per agreed tasks
2026-04-28 | Internal Demo |  |  |  | Reworking audio per new requirements
2026-04-30 | Last lab
2026-05-01 | Public demo
2026-05-03 | Final report